## Project Tracking
ADS 506¦ Final Project - Group 1
| Team | Graham Ward, Jun Clemente & Sasha Libolt
| Instructions Link: | Final Team Project
| PROJECT DETAILS |  |  |  | DELIVERABLES
| STATUS | TASK | ASSIGNEE | CATEGORY | NOTES | % DONE
M2 |  | DUE BY: | 2025-01-20 |  |  | 100%
| Done | Setup Github | Jun | Other | https://github.com/junclemente/ads507-finalproject | 100%
| Done | Setup Google Drive | Sasha | Other | https://drive.google.com/drive/u/3/folders/1bTG7DldPyUweUCLueAR-NjtXGn--ApyM | 100%
| Done | Define Business Problem / Scope | ALL | Decision |  | 100%
| Done | Select Datasets | ALL | Other |  | 100%
| Done | Create Project Plan | Sasha | Other |  | 100%
| Done | Project Proposal, DRAFt | ALL | Other |  | 100%
M3 |  | DUE BY: | 2025-01-27 |  |  | 100%
| Done | Submit Project Proprosal | Sasha | Other |  | 100%
| Done | Review Example Projects | ALL | Other |  | 100%
| Done | Assign Coding | ALL | Decision |  | 100%
M4 |  | DUE BY: | 2025-02-03 |  |  | 100%
| Done | Write scripts to fetch data from APIs and create RAW tables | Jun | Coding |  | 100%
| Done | Setup an Azure space we all share | Jun | Other |  | 100%
| Done | Write a blurb about the API | Jun | Paper | https://docs.google.com/document/d/1odybzvTQ1SId50SPulnSKx6UtR3Bi8D450T7J3TEPb4/edit?tab=t.0 | 100%
| Done | Create a log for each API as to timestamp when it refreshed | Jun | Coding |  | 100%
| Done | Create a single CSV file of each API for EDA purpose | Jun | Coding |  | 100%
M5 |  | DUE BY: | 2025-02-10 |  |  | 100%
| Done | Do basic EDA on datasets | Sasha | Coding |  | 100%
| Done | SQL Database setup | Sasha | Other |  | 100%
| Done | Write transformation procedure for travel table | Sasha | Coding |  | 100%
| Done | Write transformation procedure for weather table | Sasha | Coding |  | 100%
| Done | Write transformation procedure for highway | Sasha | Coding |  | 100%
M6 & M7 |  | DUE BY: | 2025-02-24 |  |  | 82.14%
| Done | Monitor script - dim vs raw refresh compare (timestamp vs updated) | Amayrani | Coding |  | 100%
| Done | Monitor script - dim vs raw refresh compare (updated vs last_refresh) | Amayrani | Coding |  | 100%
| Done | Data dictionary - raw tables | Jun | Paper |  | 100%
| Done | Data dictionary - dim tables | Sasha | Paper |  | 100%
| Done | Monitor script - API success | Jun | Coding |  | 100%
| Done | Create history tables | Jun | Coding |  | 100%
| Done | Create code Review Template | Sasha | Coding |  | 100%
| Done | Code review sign off | Sasha | Coding |  | 100%
| Done | Code review sign off | Amayrani | Coding |  | 100%
| Done | Create EER (ARchitectural) diagram | Jun | Paper |  | 100%
| Done | Code review sign off | Jun | Coding |  | 100%
| Done | data dictionary - history tables | Jun | Paper |  | 100%
| Done | Create views (no null rows) | Amayrani | Coding |  | 100%
| Done | Create Tableau Dashboard | Amayrani | Coding |  | 100%
| Done | Modify Data catalog template to be specific to project | Sasha | Paper |  | 100%
| Done | Tableau dashbaord overview in data dictionary | Amayrani | Paper |  | 100%
| Done | Map out the ELT | Sasha | Paper | Jun to review and add his part after Sasha is done | 100%
| Done | Map out ELT | Jun | Paper |  | 100%
| Done | Create the design doc | Sasha | Paper |  | 100%
| Done | Design Doc contribution | Sasha | Paper |  | 100%
| Done | Design Doc contribution | Jun | Paper |  | 100%
| Done | Design Doc contribution | Amayrani | Paper |  | 100%
| Done | Finalize Design Doc | ALL | Paper |  | 100%
| Not Started | Create video script | Sasha | Video |  | 0%
| Not Started | Create video slides | ALL | Video |  | 0%
| Not Started | Record part | Amayrani | Video |  | 0%
| Not Started | Record part | Sasha | Video |  | 0%
| Not Started | Record part | Jun | Video |  | 0%

## ProjectReview
Project Link | Notes
https://github.com/amcarr-ds/Climate_report_data_engineering_proj/ | Took CSV files and loaded into a mysql database
https://github.com/Pii-USD/ADS507/b | They took an api, put it in azure, then created a database. This project includes a design doc
https://github.com/sfreagin/ADS507_airlines | Includes their ppt, video, and design document

## Decisions to Track
Data Source | https://wsdot.wa.gov/traffic/api/
| access code: | 859d1329-975f-4e1c-919a-aed80585289b